## Sheet1
Phase and Step | Duration | Starting Date | Ending Date | Kefei Wu | Yuhan Yin | Yuan Li | Jiaxin Hu | Mingxi Chen | Rongjia Li
1 Team building | 1 | 2018-03-15 | 2018-03-16
1.1 Team meeting | 1 | 2018-03-15 | 2018-03-16 | Lead | Join | Join | Join | Join | Join
1.2 Tasks division | 1 | 2018-03-15 | 2018-03-16 | Lead | Join | Join | Join | Join | Join
1.3 Cooperation method selection | 1 | 2018-03-15 | 2018-03-16 | Lead | Join | Join | Join | Join | Join
2 Requirement specification | 12 | 2018-03-16 | 2018-03-27
2.1 Requirement collection | 3 | 2018-03-16 | 2018-03-18 | Lead | Join
2.2 Requirement communication | 2 | 2018-03-19 | 2018-03-20 | Lead | Join | Join | Join | Join | Join
2.3 Requirement Analysis | 5 | 2018-03-21 | 2018-03-25 | Join |  | Lead | Join | Join | Join
2.4 Requirement Confirmation | 2 | 2018-03-26 | 2018-03-27 | Lead | Join | Join | Join | Join | Join
3 High-Level design | 6 | 2018-03-28 | 2018-04-03
3.1 Prototype design | 1 | 2018-03-28 | 2018-03-28 |  |  |  |  | Lead | Join
3.2 Business architecture design | 2 | 2018-03-29 | 2018-03-30 | Lead |  | Join | Join
3.3 System architecture design | 2 | 2018-03-31 | 2018-04-01 |  |  | Lead | Join | Join | Join
3.4 Database design | 1 | 2018-04-02 | 2018-04-03 |  |  |  | Lead |  | Join
4 Detailed design | 6 | 2018-04-04 | 2018-04-09
4.1 Process flow design | 2 | 2018-04-04 | 2018-04-05 |  |  |  |  | Lead | Join
4.2 Class design | 2 | 2018-04-06 | 2018-04-07 |  |  | Lead | Join | Join | Join
4.3 Data flow design | 2 | 2018-04-08 | 2018-04-09 |  |  |  | Lead |  | Join
5 Environmental construction | 2 | 2018-04-11 | 2018-04-12
5.1 Database building | 1 | 2018-04-11 | 2018-04-11 |  |  |  | Lead |  | Join
5.2 Server building | 1 | 2018-04-12 | 2018-04-12 |  |  | Lead |  | Join
5.3 Development building | 1 | 2018-04-12 | 2018-04-12 |  |  | Lead | Join | Join | Join
6 Coding | 45 | 2018-04-13 | 2018-05-27
6.1 Front-end | 25 | 2018-04-13 | 2018-05-07 | Join | Join |  |  | Lead | Join
6.2 Back-end | 30 | 2018-04-23 | 2018-05-23 |  |  | Lead | Join | Join
6.3 Database | 30 | 2018-04-28 | 2018-05-27 |  |  | Join | Lead | Join
7 Testing | 31 | 2018-05-29 | 2018-06-29
7.1 Unit testing | 7 | 2018-05-29 | 2018-06-04 |  |  | Lead | Join | Join | Join
7.2 Integration testing | 7 | 2018-06-06 | 2018-06-12 |  |  | Lead | Join | Join | Join
7.3 System testing | 7 | 2018-06-13 | 2018-06-19 |  |  | Lead | Join | Join | Join
7.4 Acceptance testing | 7 | 2018-06-20 | 2018-06-26 | Lead | Join | Join | Join | Join | Join
7.5 Testing report | 2 | 2018-06-27 | 2018-06-28 |  |  | Join |  | Lead | Join
8 Project Delivery | 3 | 2018-06-29 | 2018-07-01
8.1 User document | 1 | 2018-06-29 | 2018-06-29 | Lead | Join |  |  | Join
8.2 Project promoting | 2 | 2018-06-30 | 2018-07-01 | Lead | Join | Join | Join | Join | Join