## Sheet1
Days
1 Team building | 2018-03-15 | 1
1.1 Team meeting | 2018-03-15 | 1
1.2 Tasks division | 2018-03-15 | 1
1.3 Cooperation method selection | 2018-03-15 | 1
2 Requirement specification | 2018-03-16 | 12
2.1 Requirement collection | 2018-03-16 | 3
2.2 Requirement communication | 2018-03-19 | 2
2.3 Requirement Analysis | 2018-03-21 | 5
2.4 Requirement Confirmation | 2018-03-26 | 2
3 High-Level design | 2018-03-28 | 6
3.1 Prototype design | 2018-03-28 | 1
3.2 Business architecture design | 2018-03-29 | 2
3.3 System architecture design | 2018-03-31 | 2
3.4 Database design | 2018-04-02 | 1
4 Detailed design | 2018-04-04 | 6
4.1 Process flow design | 2018-04-04 | 2
4.2 Class design | 2018-04-06 | 2
4.3 Data flow design | 2018-04-08 | 2
5 Environmental construction | 2018-04-11 | 2
5.1 Database building | 2018-04-11 | 1
5.2 Server building | 2018-04-12 | 1
5.3 Development building | 2018-04-12 | 1
6 Coding | 2018-04-13 | 45
6.1 Front-end | 2018-04-13 | 25
6.2 Back-end | 2018-04-23 | 30
6.3 Database | 2018-04-28 | 30
7 Testing | 2018-05-29 | 31
7.1 Unit testing | 2018-05-29 | 7
7.2 Integration testing | 2018-06-06 | 7
7.3 System testing | 2018-06-13 | 7
7.4 Acceptance testing | 2018-06-20 | 7
7.5 Testing report | 2018-06-27 | 2
8 Project Delivery | 2018-06-29 | 3
8.1 User document | 2018-06-29 | 1
8.2 Project promoting | 2018-06-30 | 2